## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a admission desk executive /pharmacist/ diagnostic center executive I want to be able to log in the hospital website with my user ID and password So that I carry out my transactions | Task 1 | Kiran Chandra | Write a program for displaying the home/login page | 6 | 3 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for the Home page /login page | 6 | 3 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Create and Connect the DB fields for login page | 5 | 3 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | Write test cases,execute the tests | 3 | 2 | 1 | 1 | 0 | 0 | 0 | Closed
US002 | As a admission desk executive I want to be able to capture new patient information So that I can create a new patient in the system | Task 1 | Kiran Chandra | Write a program to capture new patient records | 6 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the add new patient page | 6 | 3 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Design the backend logic for verification | 5 | 3 | 1 | 1 | 0 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | Write test conditions, execute the tests/manual tesing | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Closed
US003 | As a admission desk executive I want to be able to edit existing patient information So that I can store the updated patient information in the system | Task 1 | Kiran Chandra | Define the route in flask for update patient page | 6 | 4 | 2 | 1 | 0 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for Update page | 6 | 4 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Update the appropriate fields in database | 5 | 3 | 2 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | check for corner/edge cases/ manual testing | 3 | 2 | 2 | 1 | 0 | 0 | 0 | Closed
US004 | As a admission desk executive I want to be able to delete/discharge existing patient from system | Task 1 | Kiran Chandra | Write the program to get the data and verify the ID | 6 | 5 | 4 | 2 | 1 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI page for Delete view | 6 | 5 | 4 | 2 | 1 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Delete the entry and verify the deletion action | 5 | 4 | 3 | 2 | 1 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | check for corner/edge cases/manual testing | 3 | 3 | 3 | 2 | 1 | 0 | 0 | Closed
US005 | As a admission desk executive I want to be able to view all the active patients currently admitted in the hospital | Task 1 | Kiran Chandra | Write the privileges to check logged users | 6 | 6 | 5 | 3 | 2 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for displaying the details | 6 | 6 | 2 | 2 | 1 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Deserailize the DB fields for front end use | 6 | 6 | 3 | 2 | 0 | 0 | 0 | Closed
|  | Task 4 | Nishant Kumar | Write test conditions to test, execute the tests/manual testing | 3 | 3 | 2 | 2 | 1 | 0 | 0 | Closed
US006 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | Task 1 | Kiran Chandra | Verify the logged in user access privileges | 5 | 5 | 5 | 3 | 2 | 0 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design UI for search patient screen and displaying the details | 5 | 5 | 5 | 2 | 1 | 0 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Deserailize the DB fields for front end use | 5 | 5 | 4 | 2 | 1 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | Write test cases /manual testing | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Closed
US007 | As a pharmacist I want to be able to capture the medicines issued to a patient So that I can issue new medicines for an existing patient | Task 1 | Kiran Chandra | Get the ID from front end and counter verify the ID | 6 | 6 | 5 | 4 | 2 | 1 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI for a 'issue medicines' screen | 5 | 5 | 5 | 4 | 2 | 1 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Create a DB table to issue medicines | 4 | 4 | 4 | 2 | 1 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | Write test cases /manual testing | 2 | 2 | 2 | 2 | 2 | 1 | 0 | Closed
US008 | As a diagnostics executive I want to be able to capture the diagnostics conducted to a patient So that I can add new tests for an existing patient | Task 1 | Kiran Chandra | Get the ID from front end and counter verify the ID to add new tests | 6 | 6 | 6 | 4 | 3 | 2 | 0 | Closed
|  | Task 2 | Anuj Kumar | Design the UI to display diagnostics | 6 | 6 | 6 | 4 | 2 | 2 | 0 | Closed
|  | Task 3 | Pradeep Kumar | Create and Connect the DB fields to add new tests | 5 | 5 | 5 | 3 | 2 | 0 | 0 | Closed
|  | Task 4 | Pooja Pakolu | Check for corner/edge cases/manual testing | 3 | 3 | 3 | 3 | 2 | 2 | 0 | Closed
US009 | As a admission desk executive I want to be able to get existing patient information So that I can raise the bill for the patient | Task 1 | Anuj Kumar | Design the UI to display diagnostics | 6 | 6 | 6 | 6 | 6 | 4 | 0 | Closed
|  | Task 2 | Pradeep Kumar | Get and deserialize the data for display | 6 | 6 | 6 | 6 | 6 | 4 | 0 | Closed
|  | Task 3 | Kiran Chandra | generate the patient bill and allow to print bill in PDF format | 5 | 5 | 5 | 5 | 5 | 3 | 0 | Closed
|  | Task 4 | Pooja Pakolu | Check for corner/edge cases/Manual Testing | 3 | 3 | 3 | 3 | 3 | 2 | 0 | Closed
| Deploy the application | Task 5 | Anuj Kumar | Prepare UI for production | 5 | 5 | 5 | 5 | 5 | 5 | 0 | Closed
|  | Task 6 | Pradeep Kumar | integrate the code | 5 | 5 | 5 | 5 | 5 | 5 | 0 | Closed
|  | Task 7 | Kiran Chandra | Check the code and push to github | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Closed
|  |  |  | Total | 187 | 160 | 133 | 100 | 62 | 35 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
187 | 160 | 133 | 100 | 62 | 35 | 0